## Thesis Draft Schedule
Master's Thesis and Coursework Planner |  |  |  |  | Project start: | [7 empty] | 2026-08-01
Advisor: Matt Ferner | Student: Savannah K. Miller |  |  |  | Display week: | [7 empty] | 4
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html |  |  |  |  | 2026-08-17 | [6 empty] | 2026-08-24 | [6 empty] | 2026-08-31 | [6 empty] | 2026-09-07 | [6 empty] | 2026-09-14 | [6 empty] | 2026-09-21 | [6 empty] | 2026-09-28 | [6 empty] | 2026-10-05
TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2026-08-17 to 2026-10-11
 | time axis 2026-08-17 to 2026-10-11
Final Master's Thesis
Methods (Committee Ready) | Savannah | 50% | 2026-08-01 | 2026-09-13
Results-RQ 1 (Committee Ready) | Savannah | 65% | 2026-08-01 | 2026-09-13
Results-RQ 2 (Committee Ready) | Savannah | 65% | 2026-08-01 | 2026-09-30
Results-RQ 3 (Committee Ready) | Savannah | 65% | 2026-08-01 | 2026-09-30
Discussion/Introdcution/Literature Review (Committee Ready) | Savannah | 0% | 2026-09-15 | 2026-10-11
Full Draft (Advisor) | Savannah | 0% | 2026-10-11 | 2026-10-15
Full Draft (Committee) | Savannah | 0% | 2026-10-26 | 2026-10-31
Edits-Incorporation from Committee | Savannah | 0% | 2026-10-31 | 2026-11-16
Final Edits Made for Thesis To Submission! | Savannah | 0% | 2026-12-05 | 2026-12-11
Defense Presentation
Outline With Each Slide Takeaway | Savannah | 0% | 2026-09-12 | 2026-09-30
Title | Savannah | 0% | 2026-09-12 | 2026-09-30
Figures | Savannah | 0% | 2026-10-15 | 2026-11-16
Narrative | Savannah | 0% | 2026-10-15 | 2026-11-16
Review (From Advisor) | Savannah | 0% | 2026-11-16 | 2026-11-20
Practice and Edits | Savannah | 0% | 2026-11-20 | 2026-11-30
Announce Thesis Defense (Biology Department | Savannah | 0% | 2026-11-16 | 2026-11-20
Thesis Defense Presentaton | Savannah | 0% | 2026-11-30 | 2026-12-04
AGU Poster
Poster Outline | Savannah | 0% | 2026-09-12 | 2026-09-30
Title | Savannah | 0% | 2026-09-12 | 2026-09-30
Figures | Savannah | 0% | 2026-10-15 | 2026-11-16
AGU Requirements | Savannah | 0% | 2026-10-15 | 2026-11-16
Narrative | Savannah | 0% | 2026-10-15 | 2026-11-16
Review (From Committee) | Savannah | 0% | 2026-11-16 | 2026-11-30
Print | Savannah | 0% | 2026-11-30 | 2026-12-04
Presentation | Savannah | 0% | 2026-12-07 | 2026-12-11
Insert new rows ABOVE this one
Formulas:
Display week: = [Display week:, row below]